STOTTESDON&SIDBURY PARISH COUNCIL PARISH PLAN 2012 - PRIORITIES AND PROPOSED ACTIONS (v2May12)

| PRIORITY | ACTION | PARTNERS/LEAD AGENCY | TIMESCALE | RESOURCE | PROGRESS |
| --- | --- | --- | --- | --- | --- |
| Road Maintenance | - PC to monitor condition and report problems to SC - Lengthsman scheme to continue | Shropshire Council/Parish Council | ongoing | PC time/SC budget | 2012/13 Road maintenance programme provided by SC. Stottesdon road inspection due 2012 |
| GP Surgery | - Additional parking to be identified - PC to support practice in enlargement of building | NHS/PC | Tbc in liaison with practice | Tbc |  |
| Accident and Emergency | - First responders: status check to be made and link with GP surgery explored - Acute Services: Respond to consulltations on future provision - Ambulance service: monitor response times and effectiveness new systems | NHS/PC | 2012 As appropriate 2012/13 | PC time |  |
| School development | - Support Stottesdon Primary School in delivery of its development plan, including new initiatives and partnerships - Support initiatives to improve access to post-16 education | SC/School/PC | Ongoing | PC time |  |
| Facilities for Children and Young People | - Identify land to provide outdoor sports and play facilities - Prepare bids to potential funding sources and plan use of facilities - Support improvement of accommodation for playgroup - Explore options for supporting youth outreach work locally, via premises/transport/coordination | SC/School/ Playgroup/PC | 2012 | 1&2. PC time 3.PC funding 4. PC time/funding, as appropriate |  |
| Providing Family Homes | - Undertake housing needs survey | Parish Council | June 2012 | PC time |  |
| Opportunities for local Jobs and Businesses. | - Work with local employers to support and develop local training and apprenticeship schemes - Promote government funding for farming and other rural businesses - Explore possibility of local support for people re/entering workforce | Parish Council/local businesses/DWP | 2012/ ongoing | PC time |  |
| Shop Retention | - Support shop committee to establish community shop - Investigate options for Post Office provision | Shop Committee/PC | 2012 | PC time/funding | Work of shop committee well advanced; market research to be undertaken soon. |
| Scenic Views and Natural Habitats | - Support for farming and local businesses - Support initiatives to keep river clean and clear - Support initiatives to control litter - Maintenance footpaths and signage | PC PC/Willowdene PC/School/Willowdene P3 group/PC | ongoing | PC time |  |
| Policing and Community Safety | - Liaise with police re planned changes to service - Improve communication with police - Ascertain implications new Police and Crime Commissioner - Continue to promote dangers speeding vehicles | PC/Parish Watch/ LJC | 2012 2012 2012 ongoing | PC time | - PCC to be elected November 2012 |